National Iranian Oil Company Safety, Health and Environment Management Guideline for Pre-Startup Safety Review Reviewing Translation; Confirmed by; Publication Date of English Version. Davood Naderi/ Laleh H. Abbasi Training & Performance Measurement Department; Mani Abdollahzadeh Rad/ HSE Manager; September 2018. Responsibility/Subject; Prepared by; Confirmed by; Approved by; Publication date. Name; Mani Abdollahzadeh/ Fereshte Miraj Head of Safety and Firefighting Department /Project Supervisor of Safety and Firefighting Department; Siavash Derafshi/ HSE Manager; Roknodin Javadi CEO; November 2015. Position. Document Code: NIOC-HSE-SF-GU-002-01 Revision date: December 5, 2015, Revision No.: 1

Contents

## Preface										3

- Objective										3

- Range of Application								4

- Basic Documents									4

- Positions and Responsibilities							5

- PSSR Study Requirements								6

  - Appropriate Time for PSSR and Determining the Scope of Studies		6

  - PSSR Checklists								6

  - Arrangement of the PSSR Team						8

  - Preparing the PSSR Study Timetable						9

  - Training and Announcing the PSSR Schedule				9

  - Inspecting the Facilities and Interviewing Key Personnel			10

  - Filling the PSSR Checklist							10

  - PSSR Report									10

  - Follow-up Meetings								11

  - Confirmation of the Final PSSR Report and Referral to the Commissioning Committee									11

- Periodical Audits and Quality Control of the PSSR Plan  				11

- References									12

- Appendices

  - Appendix A: PSSR Checklists							13

  - Appendix B: Example PSSR Follow-up Worksheet				27

  - Appendix C: Example Comprehensive PSSR Report				28

  - Appendix D: PSSR Flowchart							29

  - Appendix E: Glossary								33

  - Appendix F: Abbreviations							35

Preface

As one of its strategic objectives, the HSE and Passive Defense Directorate of NIOC promotes a preventive approach to establishing and developing the HSE management system. Commitment to HSE considerations in the initial steps of project design and development minimizes the need for future modifications during operation, helping reduce future costs effectively. Therefore, it is of utmost importance to predict the risks and adopt the necessary preventive measures at every stage of the design, construction, and installation according to the nature and prospect of the hazards. Accordingly, pre-startup is one of the most important and critical steps from the perspective of the risks and potential accident, urging the need for an in-depth identification and prediction of the risks to determine the faults and inconsistencies in design and installation so that accidents are minimized during the startup are minimized and a safe operation is ensured. To this end, the PSSR is among the most important manuals to be accurately followed in the facilities before their startup and operation.

In this regard, the Pre-Startup Safety Review (PSSR) guideline was prepared in 2013 by the HSE and Passive Defense Directorate of NIOC and communicated by the former CEO of NIOC. This document described the PSSR study process in detail and specifies the requirements for project execution. The document was revised in 2016 with its first edition prepared with the aim of complementing and specifying the minimum PSSR study requirements to ensure the safe operation of all new facilities, development plans, and projects, as well as those units to be put into service after a long halt. Therefore, all safety and process requirements in design, construction, and installation are controlled again before unit startup to maintain design integrity.

In fact, this procedure can be interpreted as the final confirmation before the initial startup and as the second protection layer for the safe startup of facilities.

The depth or level of PSSR studies depends on the risks involved in the process, the extent of the project, the halt duration of the unit and its time of return back to service.

Important note: According to this guideline, the subsidiary executives and operating companies of the NIOC are obligated to codify the institutionalization procedure and the requirements for the implementation of the said document in their respective companies in the form of a "PSSR Manual”.

2. Objective

The objective of preparing and implementing this guideline is to guarantee a safe startup and operation for all the facilities and make sure the system, equipment, and personnel are prepared before the startup by:

- Identifying and predicting the risks involved to startup the facilities with the minimum accidents.

- Ensuring all the required actions are taken in accordance with the defined design specifications in all the stages of construction, equipment installation, and repair.

- Ensuring all safety, operation, and repair manuals, as well as the emergency response plan (ERP), are already implemented and at hand.

- Ensuring all the corrective recommendations and the modifications suggested by risk studies in different stages of the project are implemented (including HAZOP and HAZID).

- Updating the safety information and documents

- Assessing the preparedness of the personnel for a safe operation.

3. Range of Application

This guideline is irrevocable in the following form in all the subsidiary companies, oil and gas operating companies, and the operation fields of the NIOC and its contractors:

- All projects, new facilities, and development plans in the subsidiaries and operating companies of the NIOC

- Relaunching (including operation and putting into service) of the facilities and equipment after a long halt or major maintenance turnaround

In general, any change made to the system, that somehow affects the process information (parameters such as operation, capacity, and operational plans), equipment information (mechanical, electrical, and type), and/or safety information (creating new risks), requires a PSSR study.

4. Basic Documents

The following documents must be prepared and accessible by the team members as a prerequisite for the PSSR study.

- Risk assessment documents, SIL, FMEA, HAZOP PHA, and HAZID.

- Process maps, Piping and Instrument Diagrams (P&ID), PFD5, …

- Documents regarding errors in different sections related to the study such as the trip matrix, ESD narratives, the potential of hazards, the consequences of failure, maintenance frequency.

- Safety and operating manuals

- Emergency response documents

- Management of change (MOC) documents

- Startup procedure and the documents on the possible corrections at the startup time.

- Area classifications

- Documents and papers on the conformity of mechanical, electrical, and structural statuses and instruments.

- Safety data sheet (SDS)

5. Positions and Responsibilities

As the PSSR process owner, the HSE directorate of the NIOC will supervise the implementation of this guideline and is responsible for revising and updating it. The highest level authorities in the subsidiary and operating companies of NIOC are responsible for putting this guideline into practice. According to this guideline, the subsidiary executive and operating companies of the NIOC are obligated to codify the internalization procedure and the requirements for the implementation of the aforementioned document in their respective company in accordance with their activities and organizational structure in the form of a "PSSR Manual".

5.1. Company CEO

The CEOs of the subsidiary companies are in charge of the following in addition to the projects and development plans defined within the scope of their responsibility:

- Ensuring the execution of the PSSR manual in accordance with the defined requirements in this documents by defining the duties and responsibilities of the line managers.

- Ensuring that no modification, and development or equipping project enters the commissioning and startup stages after a long halt unless the required PSSR studies are conducted.

- Supporting the PSSR study team.

5.2. Plan Executor/Project manager

The executors of development plans or project managers are responsible for the following:

- Following up on the PSSR studies and supervising the quality execution of the studies in accordance with the defined requirements.

- Fulfilling the legal obligations and issuing the PSSR manual certificates.

- Specifying the main roles and responsibilities required for the PSSR, for example, PSSR coordinator and team leader.

- Planning and holding the required training courses for implementation of PSSR.

- Ensuring that the personnel is aware of their role and duty in implementing the requirements of this guideline and contributing to promoting the HSE management system.

- Following up the execution of PSSR reports and justify the plan/project contractor on fulfilling the legal obligations regarding the execution of PSSR studies before startup.

5.3. HSE Offices

- Participating in the PSSR sessions as the chief member.

- Coordination and consultation with the respective units for the correct implementation of the PSSR requirements.

- Auditing the implementation of the PSSR manual so as to meet the minimum requirements.

- Cooperating in educating the PSSR manual to reach a mutual understanding and identical perception.

- Following up, controlling, and supervising the implementation of the results of the PSSR studies in the operating units to identify the differences between the recommendations and implementations, and suggesting ways to reduce the potential deviations.

- Confirming the final PSSR report and referral to the commissioning and startup committee.

6. PSSR Study Requirements

6.1. Appropriate Time for PSSR and the Scope of Studies

The time for conducting PSSR studies is an important subject since they are key studies in the commissioning stage before plan startup. The PSSR studies regarding all the EPC contracts and development plans and projects that are in the commissioning and startup stage must be conducted before hand-over to the operator is completed.

6.1.1. The PSSR study shall not be conducted before the mechanical activities of the project are finished and the prerequisite documents are prepared. Therefore, to coordinate and plan the study, it is necessary to hold a number of internal meetings to assess the level of preparation for the execution of PSSR. In the technical meetings attended by the representative of the operator and commissioning team (on behalf of the employer and contractor), before planning the studies, the key questions about the completion of mechanical activities, construction, and the readiness of the unit should be raised and answered by the operator's representative, based on which the execution procedure is then planned. Moreover, the scope of inclusion and extent of PSSR studies, including the priority of the sections for PSSR study and the sections with no need for PSSR, are determined in these meetings.

6.1.2. PSSR studies are necessary for the units returning back to service after a long halt or fundamental repairs, before the startup.

6.2. PSSR Checklists

Considering that the PSSR study and all the discussions in the PSSR meetings are based on PSSR checklists, the second important point in the development and accurate conduction of a PSSR study is to select appropriate checklists. A specific and practical checklist must be designed according to the type, nature, and extent of the project under study.

Comprehensive checklists are usually selected in the case of large, new development plans. However, in other cases where making a change in the operating process is the reason for conducting the PSSR study, simpler checklists may also be used. In general, the checklist design process has the following steps:

- Examining the existing checklists and selecting those most applicable to the current project.

- Prioritizing and determining the order of the activities to be carried out.

- Separating the specified activities and deciding how to assess and plan them.

- Registering the state of the activities under study.

- Assigning responsibilities and estimating the time of completion.

When designing and preparing the checklist, it should be noted that all the related aspects (i.e. process type, technology, personnel, project execution plan, operation time, etc.) are taken into consideration and the followings are covered as far as possible.

- Process Safety Information (PSI): Interviewing the key personnel and investigating the documents based on the process design information, equipment, material hazards, maps, etc. to satisfy the design criterion as well as updating the safety information.

- Results of Risk-Assessment Studies: Ensuring the hazards are identified and evaluated and verifying all the measures proposed by risk assessment studies are in place before the startup.

- Standard Operation Procedure and Safer Work Practice: Ensuring that all safety, operation, maintenance & repair, and emergency response manuals are prepared, approved, and properly executed. These manuals must be in line with the process safety documents and the recommendations of the risk studies.

- Mechanical Integrity: Ensuring that periodic test and inspection of the equipment, reliability & logic of interlocks, preventive maintenance, etc. are carried out systematically.

- Quality Assurance: Ensuring quality assurance manuals are available and executed for critical prefabricated equipment according to design specifications.

- Construction: Ensuring that the mechanical construction of the equipment is finished and their installation and assembly are carried out properly for a safe startup.

- Punch List: Re-controlling the punch lists to ensure all actions required for the startup of a unit, including mechanical, electrical, and control actions, are finished before commissioning meetings.

- Change Management: Ensuring that a comprehensive system exists to investigate and confirm the changes made by individuals and their eligibility and to register them appropriately (for example, updating the operational maps).

- Human Resources: Ensuring that competent, sufficiently-experienced, and skilled individuals Shielding in the first months of project startup.

- Training: Ensuring that individuals are trained on topics such as knowledge of operation manuals, operations fundamentals, the appropriate reaction to an emergency, process information, and HSE hazards so that the personnel is fully prepared at the time of startup.

- Contractors: Ensuring that the contract employees are trained and aware of important hazards such as fire, explosion, and leakage of toxic substances in the working environment.

- Equipment Register: Ensuring that the pressure vessels, discharge systems, radioactive sources, lifting equipment, and safety instrumentation systems are registered according to legal requirements and standards.

- Analysis of Accidents: Ensuring that an analysis and investigation manual exists and following up on the adoption of the recommendations and corrective measures.

- Emergency Reaction Plan: Ensuring that an emergency reaction plan or manual exists, individuals are trained to handle emergency situations, maneuvers are planned and performed for important accidents based on risk assessment studies to identify the weaknesses and following up on the adoption of corrective measures.

- Auditing: Planning audits according to the auditing regulations and manuals approved by the respective company.

An example PSSR checklist suitable for large projects and important development plans is provided in Appendix A. The study credentials are entered in the first part of the checklist, and the remaining fields classify the PSSR investigation items in the five following categories. Note that the topics discussed in each category can be modified depending on the process type and project nature.

- Plant design integrity

- Occupational safety and health

- Process safety management

- Accident management

- Commissioning readiness

6.3. Arrangement of the PSSR Team

For a successful PSSR study, it is necessary to assemble a team of competent, knowledgeable, and experienced individuals from different fields of expertise to carry on the study through teamwork.

The teams attending the PSSR meetings and responsible for conducting the study may be composed of people coming from different areas of expertise depending on the type of the study. A team of two or three will suffice for cases of PSSR studies due to small modifications made to the system. However, in large projects and/or development plans, it is necessary that the PSSR team is composed of specialists from different fields depending on the type of study. The success of the PSSR study largely depends on planning the arrangement of the team and selecting its members.

The key roles in the PSSR studies, based on which the need for different expertise is assessed, are as follows:

- Team Leader: Responsible for directing PSSR meetings and assigning members their duties.

- Coordinator: Responsible for confirming the completion of the PSSR report before unit startup.

- PSSR Team Members: The team members are responsible for the execution and investigation of PSSR items according to the schedule. The team is composed of individuals from different sections including process, startup, operation, maintenance, mechanics, electrics, instrumentation, and HSE.

6.3.1. When conducting PSSR studies, a person is selected as the leader with full responsibility and authority. The role of a leader is crucial in the effective progress of PSSR meetings. The leader is expected to be an independent person, experienced and skilled in leadership and execution of studies, who shall be selected carefully under the supervision of the main employer of the project (i.e. the plan executor). Moreover, the team leader is to make sure that the PSSR team members are technically competent and appropriately skilled and experienced.

6.3.2. Depending on the type of the study, the team may be divided into multiple task groups with their own leadership, so that the PSSR study can be performed segment by segment. Ultimately, the task-group leaders report back to the team leader for the conclusion of the study. The team leader is responsible for determining the task groups and assigning them tasks and responsibilities and selecting their leaders.

6.3.3. Depending on the topic of the meetings and studies, specialists from other sections may attend the PSSR meetings as part-time members.

6.3.4. Experienced, outsourced consultants may also be employed in cases where changes made to the unit lead to new hazards in the process or the environments.

6.4. Preparing the PSSR Study Timetable

In each study, the PSSR coordinator and the team leader are to prepare a schedule for the committees involved in the study through thorough research based on the designed checklist with respect to the project planning and adoption of corrective measures before the startup. This schedule specifies the person in charge of each activity defined in the checklist as well as the predicted deadline for each activity. The team leader is expected to personally follow up and supervise everything based on this schedule.

6.5. Training and Announcing the PSSR Schedule

In advance of PSSR meetings, the team members must be well-trained and fully aware of their allocated obligations and tasks. In general, the PSSR training and the knowledge of the schedule should be planned and executed at four levels targeting the following groups:

- Team leader and PSSR task group leaders.

- PSSR team members

- Management personnel of the studied unit

- Other individuals (operation, maintenance, etc.)

6.5.1. The method of training (i.e. classroom, electronic, individual, self-study, workplace) must be listed in the training profile of the trainees.

6.6. Inspecting the Facilities and Interviewing Key Personnel

Inspection is another requirement of the PSSR study. To ensure the fulfillment of all PSSR requirements, the PSSR team members are expected to inspect the studied unit as many times as necessary. These inspections are usually planned in coordination between the PSSR team leader and the person in charge of the unit. Some of the items to be controlled and investigated during the inspections are as follows:

- Ensuring that construction and installation stages were carried out in compliance with design specifications.

- Identifying the physical, mechanical, and chemical hazards such as scaffolding, illumination, sound, ventilation systems, grounding system, collapse, and leakages.

- Confirming the readiness of safety and fire suppression systems such as interlocks, gas detectors, deluge system, fire suppression foam and cooling systems, and safety eyewash stations.

6.7. Filling the PSSR Checklist

After completing the PSSR study, all checklists shall be filled and signed by the PSSR team members and then confirmed by the project executive/manager. The checklist assessment result is then expressed through one of the following statements:

- The unit is safe for startup.

- The unit is safe for startup only if the deficiencies are resolved and the corrective recommendations are applied.

- The unit is not safe for startup.

Typically, the deficiencies, suggestions, and the corrective measures in reports are one of the two types:

Group A: Pre-startup requirements, which must be completed before startup.

Group B: The second priority items, which may be dealt with after startup.

To ensure the corrective recommendations and measures are adopted, after the study is over and completing the checklists, the office/unit authorities who are responsible for these issues must meet with the team and task-group leaders and set a date for resolving each deficiency and putting corrective measures into effect.

6.8. PSSR report

Ultimately, the PSSR report is prepared by the team leader based on the checklist items, inspection reports, and the list of corrective actions and then sent to the commissioning committee after final confirmation. An example PSSR report can be found in Appendix B.

6.9. Follow-up Meetings

To ensure everything is in place for a safe unit startup, periodic follow-up meetings should be held and continued after preparing the PSSR report until all PSSR requirements and standards are met. A list of all the remaining issues and the respective corrective measures is discussed in these meetings and the priority of each action in the startup is determined. An example PSSR follow-up worksheet is provided in Appendix C.

Moreover, PSSR team members will inspect the studied unit as scheduled to ensure all of the requirements of the PSSR report are met.

6.10. Confirming the Final PSSR Report and Referral to the Commissioning Committee

After the follow-ups, when the state of corrective measures and PSSR recommendations become clear, the final report is prepared by the team members and, after confirmation by the HSE, is sent to the commissioning and startup committee. In fact, HSE acts as a control and supervision entity to track, address, and finalize the items specified in the PSSR reports.

Moreover, the HSE office is expected to inspect the studied unit as scheduled to ensure all of the requirements of the PSSR report are met.

6.10.1. Carried out in the pre-start stage, full control and confirmation of some of the items on the PSSR checklist are subject to the initial unit startup. These items are to be mentioned clearly in the final report.

6.10.2. The items carried out after the startup must be specified clearly along with the confirmation of the respective authorities in charge.

6.10.3. As the documents confirming all the equipment are fabricated and installed correctly and tested according to design specifications, the PSSR report, as well as the respective confirmations, must be kept in an appropriate place.

6.10.4. This document of confirmation is considered as the prerequisite for the startup but is not the only permit required for initiating the startup. Other items are also involved that are out of the scope of this guideline.

7. Periodical Audits and Quality Control of the PSSR Plan

As one of the HSE management system documents, the quality of the performance of the PSSR guideline must be monitored and controlled. In this regard, the items to be investigated and scored in the auditing checklist are as follows:

- Emphasizing the necessity of undertaking risk studies during the design, construction, and modification of a new unit according to company policies.

- Commitment to undertaking PSSR studies as a general policy of the company and ensuring the following requirements are met before the startup of each unit, as well as equipping and putting new plans into action:

  - All of the required operation manuals

  - Training and preparedness of individuals involved.

  - Access to all inspection, maintenance, safety, and reaction manuals in emergencies.

  - Undertaking and following up on the results of the risk study.

- Complying with the requirements of the PSSR manual (study conduction time, inspection, etc.).

- The necessity of preparing inspection reports and confirming the compliance of every item with the design and construction specifications, as well as the standards, regulations, and other requirements.

- Reporting the identified inconsistencies and resolving the hazardous situations in the work environment.

- Emphasizing on the PSSR confirmation document as the prerequisite for starting up new development plans and projects.

8. References

1. Guidelines for performing effective pre start up safety reviews, CCPS, 2007.

2.  Pre start up safety reviews (operational process), ASPC.

3. PSSR Report، Uhde، MD/HDPE PARS, 2007.

4. PSSR‐Pre start up safety review, Sasol, SI‐SHERQ‐6.02.

9.1. Appendix A: PSSR checklists

| PSSR Checklist |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Study type | Development Plan/Project □ Process change □ |  | Study date: |  | Study code: |  | Project code: |
| Study title | Scope: |  |  |  |  |  |  |
| Team leader |  |  |  |  |  |  |  |
| Investigated items | Recommendations |  |  |  |  |  |  |
|  | - Conformity of the fabrication and installation of the equipment to design specifications. - Fitness of the manuals, regulations, rules, operation methods, maintenance, HSE, and reaction to emergencies (comprehensive and thorough) - Results of risk assessment studies to ensure their execution - Full preparedness of all the employees involved in the project (investigating training records, competency, and experience) |  |  |  |  |  |  |
|  | Investigation results |  | Recommendations |  |  |  |  |
|  | - The unit is safe for startup - The unit is safe for startup only if the recommendations are applied - The unit is not safe for startup. |  |  |  |  |  |  |
| Investigation team |  |  |  |  |  |  |  |
| Name |  | Position |  | Date |  | Signature |  |

| Row | Revision Team/Requirements | State |  |  |  | Corrective Measures/Recommendations | Degree of Importance | Person Responsible for Action | Deadline |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Yes |  | No |  |  | (A/B) |  |  |
| - Plant Design Integrity |  |  |  |  |  |  |  |  |  |
| 1 | Defining the main and secondary systems in the project clearly |  |  |  |  |  |  |  |  |
| 2 | Controlling the codes and standards |  |  |  |  |  |  |  |  |
| 2.1 | Controlling the documents and records of the mechanical equipment (rotary, fixed) |  |  |  |  |  |  |  |  |
| 2.2 | Controlling the documents and records of the electrical equipment |  |  |  |  |  |  |  |  |
| 2.3 | Controlling the documents and records of control and instrumentation equipment |  |  |  |  |  |  |  |  |
| 2.4 | Controlling the structural design documents and computations |  |  |  |  |  |  |  |  |
| 2.5 | Controlling the documents and records of safety and fire suppression equipment |  |  |  |  |  |  |  |  |
| 3 | Controlling the hand over requirements (construction completion, RFS, RFSU, etc.) |  |  |  |  |  |  |  |  |
| 4 | Is there a classified and distinct punch list for every section (mechanical, control, electrical, instrumentation, etc.)? |  |  |  |  |  |  |  |  |
| 4.1 | Performing random check to control every item in Categories 1 and 2 of the punch list. |  |  |  |  |  |  |  |  |
| 5 | - Controlling the equipment inspection checklist to ensure consistency of the construction and installation- Conformity of the equipment to the design specifications - Rotary equipment - Fixed equipment - Instrumentations - Fire suppression equipment - Pipelines |  |  |  |  |  |  |  |  |

| - Occupational Safety & Health |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Conformity of the construction and installation of the equipment to design specifications |  |  |  |  |  |  |
| 2 | Compliance with safety and health regulations |  |  |  |  |  |  |
| 3 | Systematic, periodic inspection schedule |  |  |  |  |  |  |
| 4 | Safety of equipment, rotary machine, cranes, lifters |  |  |  |  |  |  |
| 5 | Standard scaffolding, ladders, and platforms |  |  |  |  |  |  |
| 6 | Assigning color codes and numbers to the equipment and safety signs |  |  |  |  |  |  |
| 7 | Registered equipment |  |  |  |  |  |  |
| 8 | Standard access paths |  |  |  |  |  |  |
| 9 | Operational electrical systems |  |  |  |  |  |  |
| 10 | Proper lighting system |  |  |  |  |  |  |
| 11 | Proper and safe access to the valves, pressure gauges, etc. |  |  |  |  |  |  |
| 12 | Removing the temporary electrical systems |  |  |  |  |  |  |
| 13 | Testing the fire protection systems |  |  |  |  |  |  |
| 14 | Personal protective equipment |  |  |  |  |  |  |
| 15 | Collective protective equipment (eye wash station shower, safety shower, etc.) |  |  |  |  |  |  |
| 16 | Personal protective devices |  |  |  |  |  |  |
| 17 | Steam system, steam tracer (installation and insulation) |  |  |  |  |  |  |
| 18 | Compressed air system |  |  |  |  |  |  |
| 19 | Nitrogen and inert gas systems |  |  |  |  |  |  |
| 20 | Marking the confined spaces |  |  |  |  |  |  |
| 21 | Grounding system for metal equipment |  |  |  |  |  |  |
| 22 | Shielding rotary machines |  |  |  |  |  |  |
| 23 | Shielding or insulating hot surfaces |  |  |  |  |  |  |
| 24 | Management of slippery surfaces and working environment |  |  |  |  |  |  |
| 25 | Safety of pits |  |  |  |  |  |  |
| 26 | Discharging emergency pollutants to a safe location (vent drain, trap, etc.) |  |  |  |  |  |  |
| 27 | Control room requirements |  |  |  |  |  |  |
| 28 | Ergonomics of the working stations |  |  |  |  |  |  |

| Row | Revision Team/Requirements | State |  |  |  | Corrective Measures/Recommendations | Degree of Importance |  | Person Responsible for Action |  | Deadline |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Yes |  | No |  |  | (A/B) |  |  |  |  |
| - Process Safety Management |  |  |  |  |  |  |  |  |  |  |  |
| 1 | Established policy, objectives, assessment tools, and measurement indices |  |  |  |  |  |  |  |  |  |  |
| 2 | Measuring the HSE indices (rates of severity and frequency of accidents) |  |  |  |  |  |  |  |  |  |  |
| 3 | Clear definition of the responsibilities (safety representative, HSE manager, legal representatives, etc.) |  |  |  |  |  |  |  |  |  |  |
| 4 | Safety meetings |  |  |  |  |  |  |  |  |  |  |
| 5 | Accident report, investigation, analysis, and follow-up system |  |  |  |  |  |  |  |  |  |  |
| 6 | Inspection schedule |  |  |  |  |  |  |  |  |  |  |
| 7 | Punishment and reward system |  |  |  |  |  |  |  |  |  |  |
| 8 | Work permits and the associated certificates |  |  |  |  |  |  |  |  |  |  |
| 9 | Management of change manual |  |  |  |  |  |  |  |  |  |  |
| 10 | Workplace safety training programs (risk assessment and knowledge of the workplace hazards, control mechanism, and registering records) |  |  |  |  |  |  |  |  |  |  |
| 11 | Assessing the results of the EIA studies |  |  |  |  |  |  |  |  |  |  |
| 12 | Investigating whether the items defined in the design, construction, and project management plans are executed |  |  |  |  |  |  |  |  |  |  |
| 13 | Ensuring the as-built process maps are up-to-date (PFD, MDF, etc.) |  |  |  |  |  |  |  |  |  |  |
| 14 | Classifying and listing hazardous areas |  |  |  |  |  |  |  |  |  |  |
| 15 | Investigating PHA studies (whether the risks identified and assessed according to a specific manual.) |  |  |  |  |  |  |  |  |  |  |
| 16 | Investigating the results of risk studies (HAZOP, SIL, etc.) |  |  |  |  |  |  |  |  |  |  |
| 17 | Conducting JSA studies on hazardous activities |  |  |  |  |  |  |  |  |  |  |
| 18 | Investigating the conduction of QRA studies |  |  |  |  |  |  |  |  |  |  |
| 19 | Risk assessment of chemicals (MSDS, HAZMAT) |  |  |  |  |  |  |  |  |  |  |
| 20 | Investigating 95% of the project design model and its conformity to the construction |  |  |  |  |  |  |  |  |  |  |
| 21 | Establishment of a Medical Surveillance Program for protecting the health of the workforce – including physical stressors, monitoring medical and sanitary issues, planned screening, sampling, etc.) |  |  |  |  |  |  |  |  |  |  |
| 22 | Job description for all positions, as well as qualification requirements |  |  |  |  |  |  |  |  |  |  |
| 23 | Description of duties in an emergency for all the personnel |  |  |  |  |  |  |  |  |  |  |
| 24 | Investigating operation manuals (including the operational guidelines and manuals for the startup, routine/non-routine operations, emergency halts, process hazards, simplified process diagrams, chemical materials of the process, safe operation limits (high/low), sampling, etc.) |  |  |  |  |  |  |  |  |  |  |
| 25 | Effective education planning (course materials and plan, the instructor, target groups, review courses, etc.) for the personnel involved in startup and operation. |  |  |  |  |  |  |  |  |  |  |
| 26 | Were the operation personnel involved in preparing the manuals? |  |  |  |  |  |  |  |  |  |  |
| 27 | Were the HSE items and the required communication channels observed in the training? |  |  |  |  |  |  |  |  |  |  |
| 28 | Investigating the arrangement of the commissioning team (are operation personnel involved in the team?) |  |  |  |  |  |  |  |  |  |  |
| 29 | Do the key personnel involved in the project have the required skills and knowledge (theoretical and practical)? |  |  |  |  |  |  |  |  |  |  |
| 30 | The training history of the personnel is recorded |  |  |  |  |  |  |  |  |  |  |
| 31 | Lockout manual |  |  |  |  |  |  |  |  |  |  |
| 32 | Trip bypass manual |  |  |  |  |  |  |  |  |  |  |
| 33 | Marking all the critical valves |  |  |  |  |  |  |  |  |  |  |
| 34 | Shift system |  |  |  |  |  |  |  |  |  |  |
| 35 | Document of control and instrumentation system (detailed description of their logic, alarms and set points, interlocks, trip, and ESD). |  |  |  |  |  |  |  |  |  |  |
| 36 | Discharge, inert, flare connections, etc. systems |  |  |  |  |  |  |  |  |  |  |
| 37 | Do the key personnel involved in the project have the required skills and knowledge (theoretical and practical)? |  |  |  |  |  |  |  |  |  |  |

| Row | Revision Team/Requirements | State |  | Corrective Measures/Recommendations | Degree of Importance | Person Responsible for Action | Deadline |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Yes | No |  | (A/B) |  |  |
| - Incident Management |  |  |  |  |  |  |  |
| 1 | Accident report and analysis systems |  |  |  |  |  |  |
| 2 | Assessment of workplace health and safety |  |  |  |  |  |  |
| 3 | Assessment of fire and explosion scenarios |  |  |  |  |  |  |
| 4 | Fire alarm systems (detectors) |  |  |  |  |  |  |
| 5 | Fire suppression systems (hydrant, sprinkler, hose reel, extinguisher). |  |  |  |  |  |  |
| 6 | Personal and collective protective equipment (airline breathing apparatus, eye wash station shower, etc.) |  |  |  |  |  |  |
| 7 | Emergency manual and action plan (emergency numbers, duties of each group, escape paths, rescue facilities, first-aid kit, etc.) |  |  |  |  |  |  |

| Row | Revision Team/Requirements | State |  | Corrective Measures/Recommendations | Degree of Importance | Person Responsible for Action | Deadline |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Yes | No |  | (A/B) |  |  |
| - Commissioning Readiness |  |  |  |  |  |  |  |
| 1 | Technology (license control, quality assurance, warranty, etc.) |  |  |  |  |  |  |
| 2 | Proper clean up (debris, O2 free, etc.) |  |  |  |  |  |  |
| 3 | Startup manual (readiness of all segments, equipment, individuals, environmental conditions, etc.) |  |  |  |  |  |  |
| 4 | Manuals for handling unexpected circumstances during startup (predicting accidents, emergency halts, etc.) |  |  |  |  |  |  |
| 5 | Organizing and defining the roles and responsibilities of different individuals and committees during the startup process (project personnel, contractors, etc.) |  |  |  |  |  |  |
| 6 | Training the personnel for full preparedness during startup |  |  |  |  |  |  |
| 7 | Insurance |  |  |  |  |  |  |
| 8 | Possible modifications of the startup process |  |  |  |  |  |  |
| 9 | Controlling and supervising simultaneous constructions |  |  |  |  |  |  |

| Appendix B. Example follow-up Worksheet |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Study type: |  |  |  | Follow-up worksheet for the deficiencies, recommendations, and PSSR actions |  |  |  | Study code: |  |  |
| Date: |  | Edition: |  |  |  |  |  | Project code: |  |  |
| Row | Requirements |  | Necessary corrective measures |  | Action Type | Degree of Importance | Responsible Department |  | Responsible Individual | Time of action |
| 1 |  |  |  |  |  |  |  |  |  |  |
| 2 |  |  |  |  |  |  |  |  |  |  |
| 3 |  |  |  |  |  |  |  |  |  |  |
| * Action type, Group A: Required for startup. These actions shall be completed before startup. Group B: Second priority actions. These actions may be postponed and completed after startup. ** Degree of importance indicates whether an action is critical. Those actions that, if delayed, hinder the on-time hand-over of the project are considered critical. |  |  |  |  |  |  |  |  |  |  |

9.3. Appendix C. Example Comprehensive PSSR Report.

9.4. Appendix D. Flowchart of PSSR process

Defining the scope of PSSR studies (2)

Conducting PSSR studies for all the new, corrective, and development projects and for starting up the units or equipment after a long halt (1)

Determining the coordinator and PSSR team leader

Holding pre-meetings to prepare for execution of PSSR (4)

Ready to Execute PSSR?

Assessing the PSSR execution criteria (5)
- Completing the mechanical tasks
- Preparing the base prerequisite documents for the study

Designing the PSSR checklist (7)

Forming the PSSR team

Completing the PSSR checklist (10)
(holding the meetings and conducting field inspections, checking the papers and certificates, etc.)

PSSR training (9)

Preparing the PSSR report (11)

A

No

Yes

Evaluating the Results of the PSSR Report

The unit is safe for startup.

The unit is not safe for startup.

Safe for startup if the recommendations are implemented

Holding follow-up PSSR meetings to resolve the deficiencies (13)

A

Have all Group (A)* action been taken in the PSSR report?

Reporting to the plan executor/project manager
- Return to Stage 5

No

Yes

Group A: Actions to be undertaken before startup.
Group B: Actions that may be undertaken after startup.

Confirming the final report, determining the actions to be taken in Group B* as well as those to be implemented after the startup process, referral to the commissioning committee

Storing the PSSR records in the safety documents

End

| Row | Responsible divisions | Amenable divisions | Support divisions | Consultation divisions | Notification |
| --- | --- | --- | --- | --- | --- |
| 1 | Plan executor (startup and commissioning committee)/project manager | CEO Plan executor | Managers of the respective staff and operational units (operations, engineering, etc.) | HSE | Training |
| 2 | startup and commissioning committee/project manager | Plan executor/project manager |  | HSE |  |
| 3 | Plan executor | Plan executor/project manager |  | HSE |  |
| 4 5 6 | Team leader/PSSR coordinator/startup and commissioning committee | Plan executor/project manager |  |  |  |
| 7 | PSSR team leader | Plan executor/project manager | HSE | HSE |  |
| 8 | PSSR team leader and coordinator and HSE office | Plan executor/project manager/coordinator |  | HSE | PSSR coordinator |
| 9 | PSSR team leader and coordinator and HSE office | Plan executor/project manager | Managers of the respective staff and operational units (operations, engineering, etc.) |  | Training |
| 10 | PSSR team | Team leader | Managers of the respective staff and operational units (operations, engineering, etc.) | The team leader selects and introduces the consultants based on the checklist items |  |
| 11 | PSSR team | Team leader |  |  |  |
| 12 | Team leader/PSSR coordinator/startup and commissioning committee | Plan executor/project manager |  |  |  |
| 13 | PSSR follow-up team HSE | Plan executor/project manager/HSE | Managers of the respective staff and operational units (operations, engineering, etc.) |  |  |
| 14 | HSE Coordinator | Plan executor/project manager/ startup and commissioning committee | Managers of the respective staff and operational units (operations, engineering, etc.) |  |  |

9.5. Appendix E. Glossary

Action plan: The results of risk assessment studies and other corrective measures that improve the safety of an operational unit and/or a project are defined in the form of an action plan.

Accident management: Defined as the systematic process of reporting, researching, analysis, and learning from accidents to prevent their reoccurrence.

Audit: An organized, independent, and codified process undertaken to determine whether the results of the activities are consistent with the planning arrangements and whether these arrangements have been effectively and appropriately executed to accomplish the organization's policies and objectives.

Commissioning: As the last stage before startup, this stage includes initial check, physical control, overall review of the documents examined in pre-startup, practical testing of the instruments and the electronic and telecommunication equipment, operational testing of equipment using an inert fluid, and some other pre-startup activities.

Commissioning committee: The committee investigating the readiness of a project before startup and its commissioning to the operation division.

Emergency Safety Devices (ESD): The control equipment and apparatus implemented to reduce the risk and consequences of the release of significant hazards in the system.

Emergency Response Plan (ERP): A codified plan to quickly and effectively react to unusual conditions such as fire, explosion, natural disasters, leakage of toxic substances, etc.

Hand over: Transferring the responsibilities from the construction stage to the production stage

Hazard: Potential harmful factors, hazards are factors that cause diseases, injury, damage to equipment/factory/product/environment and/or destroy the products and impose greater losses and costs.

Hazardous event: Unexpected accident occurring due to the outbreak of a potentially damaging factor such as gas leakage, fire, etc.

Hazard Identification (HAZID): Identification, assessment, and controlling the major safety, sanitary, and environmental hazards in an operating unit according to the checklists and through reasoning to obtain an overall view of the hazards

Hazard and operability analysis (HAZOP): A systematic and structured method to identify and assess the inappropriate performance of process equipment due to design deviations and their mutual effects on the process and operation of industrial units.

Hazardous materials (HAZMAT): Appropriate assessment and management of hazardous chemicals, including their harmful effects, their entry into the body, dealing with them, their safe transport, etc. are of great importance.

Inspection test procedure (ITP): A procedure to control installation and startup of equipment in accordance with the design specifications and requirements of the manufacturing company.

Management of change (MOC): A change management system which logs, announce, and carefully analyzes any changes occurring during the working process.

Medical surveillance program: Protecting the health of the human resources involved in the project – including physical stressors, monitoring medical and sanitary issues, planned screening, sampling, etc.)

Safety data sheet: A data sheet containing the information about substances including their physical, chemical, sanitary, and safety characteristics, as well as their usage procedure, storage, transportation, and disposal.

Occupational safety and health: Refers to the topics related to protecting the health of the human resources and preventing the potential accidents and diseases in any job.

Process description: A document about a processing unit in which the inputs (feed, catalyst, additives, side services, etc.) and outputs (the final product, the intermediate product, byproducts, waste, etc.), as well as the reaction type and procedure, are provided.

Pre-Startup Safety Review (PSSR): Re-controlling new development plans or an important change made to the unit process before its (re)operation to ensure a safe startup. This control is usually performed based on the checklists prepared in a safety management system or HSE.

Plant design integrity: A framework defined particularly to manage the operational integrity and hazardous chemical processes. Mainly focused on leakage accidents, this framework is defined in terms of principles of design, engineering, operation, and appropriate maintenance.

Pre-commissioning: Referred to the stage before commissioning, in which the following are controlled: Conformity of the design and construction, the requirements stated by the technical specifications of the equipment (static test), pipeline tests, vessels, hydro-tests to investigate the quality of welding, painting, coating, etc. The results of these investigations are used in preparing the punch list.

Process Safety Management (PMS): A systematic framework for safety management of operational systems by focusing on the hazards associated with chemical processes.

Process Hazard Analysis (PHA): An organized, systematic procedure aiming to identify the process safety weaknesses by introducing different hazard identification and risk assessment methods and their various applications. It also delineates the range of application for every method at each stage of the system life-cycle (design, operation, etc.).

Risk: Defined as the combination of the probability and severity of the consequences following the event of a hazardous accident.

Risk assessment: A structured analysis involving the systematic identification and classification of the risks associated with the human resources, environment, capital, through which the risk level is estimated to determine whether it is tolerable.

Safety Integrity Level (SIL) study: Investigating the level of risk reduction resulting from the safety and process control equipment and the instrumentation in a system.

9.7. Appendix F. Abbreviations

No. 17, Yaghma Alley, Jomhuri Eslami Avenue, Tehran.

Tel. 66726016	Fax 66709723	SMS 10007615

HSEE@NIOC.IR	HTTP://HSE.NIOC.IR