National Iranian Oil Company Safety, Health and Environment Management Overhaul HSE Guideline Reviewing Translation; Confirmed by; Publication Date of English Version. Davood Naderi/ Laleh H. Abbasi Training & Performance Measurement Department; Mani Abdollahzadeh Rad/ HSE Manager; September 2018. Responsibility/Subject; Prepared by; Confirmed by; Approved by; Publication date. Name; Mani Abdollahzadeh Rad/ Fereshte Miraj Head of Safety and Firefighting Department /project supervisor of Safety and Firefighting Department; Siavash Derafshi HSE Manager; Roknodin Javadi/ CEO; February 2016. Position. Document Code NIOC-HSE-SF-GU-008-00 Revision date: February 21, 2016, Revision No.: 1

Contents

1. Introduction 											3

2. Purpose											3

3. Scope 											3

4. Role and responsibilities 									3

4.1 The N.I.O.C.’s HSE Management 								3

4.2 Managing Director 										3

4.3 Operations Manager 									4

4.4 Overhaul Executor 										4

5. Basic overhaul documents 									4

6. Performing the overhaul process 								5

6.1 Determining the overhaul implementation scope and time 					5

6.2 Timing 											6

6.3 HSE-Plan requirements 									7

6.4 Implementation 										7

6.4.1 Repair groups 										7

6.4.2 Head of the HSE Department 								7

6.4.3 Integrated Planning Department 								9

6.4.4 Logistics Department 									9

6.4.5 Repair Planning Department 								9

6.4.6 Head of the operational unit 								10

6.4.7 Head of the Technical Inspection and Corrosion Protection Department 			11

6.4.8 General requirements 									11

6.5 Completion of overhaul process, conducting tests and Pre-Startup Safety Review (PSSR) 	11

6.6 Summarizing and analyzing data								12

6.6.1 Performance evaluation 									13

6.7 Documentation and record keeping 								13

7. References 											13

8. Relevant documents: 										13

1. Introduction

All tools, equipment and machinery used in oil and gas facilities (onshore and offshore facilities) need periodic inspection and repair due to environmental factors, overuse, depreciation, and corrosion for which specific plans need to be developed for their repair or even overhaul.

Overhaul operations are associated with potential risks that, if not detected and controlled, may lead to various and occasionally irreparable accidents. The N.I.O.C.’s HSE Department has developed the present document to prevent injuries, equipment, tool and installation damages and even explosions and fires, when performing overhauls. The subsidiaries shall develop their own “Overhaul Guideline”, based on the nature and type of their operation and in accordance with the present guideline.

1. Purpose

This guideline was developed in order to describe repair and overhaul activities and to prepare the ground for planning, control and guidance of repair operations, periodically. The aim was to ensure full observance of safety and environmental requirements, control and mitigate incidents and to achieve highest levels of productivity and efficiency at lowest cost.

3. Scope

This guideline is applicable to all N.I.O.C.’s subsidiaries, operating companies, oil and gas fields, and contracting companies.

4. Role and responsibilities

4.1 The N.I.O.C.’s HSE Management

The N.I.O.C.’s HSE Management, as the owner of this guideline, shall supervise its proper implementation. It is also responsible for reviewing and updating the guideline.

4.2 Managing Director

The highest authorities (managing directors) of the N.I.O.C.’s subsidiaries and operational companies shall ensure the proper establishment and implementation of this guideline by defining duties and tasks of sub-managers. They shall also develop some instructions and procedures to institutionalize relevant activities and implement the requirements of this document across their respective companies, based on the type of their activities, current processes and in accordance with their organizational structures.

Some of the responsibilities of the Managing Director are as follows:

- Supporting all staff members and the executive team during overhauls until complete commissioning

- Funding overhaul projects

- Interaction and cooperation with other companies to provide necessary manpower and equipment

- Ensuring the proper implementation of the contractors’ HSE requirements, in accordance with the requirements specified in the “Contractors’ HSE Management Guideline” (No. NIOC-HSE-SF-GU-005-01)

4.3 Operations Manager

4.3.1 The Operations Manager is directly responsible for the implementation and monitoring of the overhaul process. He/she shall also observe all relevant rules, regulations and requirements, such as HSE instructions, requirements and standards in order to control, reduce and prevent accidents and ensure their full implementation in the overhaul process.

4.3.2 Coordination with all relevant departments and units and organizing planning meetings.

4.3.3 Reviewing company’s overhaul schedule and providing solutions to eliminate existing problems and deficiencies.

4.3.4 Monitoring the procurement mechanism of overhaul tools and equipment.

4.3.5 Planning and coordination with other companies affiliated with the N.I.O.C. to use their facilities.

4.3.6 Monitoring the selection mechanism for experienced and qualified contractors.

4.3.7 Monitoring the overhaul implementation process and providing appropriate solutions to eliminate existing problems and deficiencies.

4.4 Overhaul Executor

The Repair and Maintenance Department (R&M Department), as the executor of the overhaul process, shall undertake the following responsibilities:

- Developing a systematic plan to perform overhaul activities within specified time periods

- Ensuring the proportionality of staff professional competence with their jobs and, if necessary, coordination with relevant departments for conducting training courses

- Ensuring staff understanding about their role and responsibilities in implementing overhaul tasks

- Cooperation with the HSE Department to examine staff in terms of their physical capabilities to perform specific tasks, such as entry to prohibited areas, working at height, etc.

- Briefing contractors on the safety requirements specified in this guideline

- Preparing lists of spare parts, equipment, consumables, manpower and services required to perform overhaul tasks

- Selecting and hiring experienced and qualified contractors and ensuring their competence

5. Basic overhaul documents

Before performing overhaul operations, the following documents shall be prepared and provided to the authorities of relevant units as prerequisites:

- HSE Risk and overhaul hazard assessment documents and their findings

- Operational unit’s reports on equipment and machinery defects

- Process Flow Diagrams (PFD), Piping and Instrumentation Diagrams (P&ID), etc.

- Guidelines and procedures for safe work practice

- Instructions for specific activities such as pipeline lining or weld back

- Safety and operational commissioning instructions

- Emergency response planning documents

- Change management documents for recording necessary changes during overhaul

- Electrical/mechanical and instrumentation drawings

- Safety Data Sheet (SDS) on chemicals

- Preparing lists of needed machinery and the relevant certification documents

- Providing the personnel with educational ID cards for overhaul and training purposes

- Preparing ID cards for equipment and recording items, including technical specifications, installation place, manufacturer serial number, property control number and repair history

- Preparing an overhaul implementation instruction

- Analyzing potential overhaul-related accidents in previous years to prevent their recurrence

- Other related activities to the nature of adopted measures by companies

6. Performing the overhaul process

The overhaul initiation is calculated based on the unit S/D time and consists of the following steps:

1. Determining the overhaul implementation scope and time

2. Overhaul planning

3 Preparing the HSE-Plan

4. Overhaul implementation

5. Completion of the overhaul process, conducting tests and Pre-Startup Safety Review (PSSR)

6. Summarizing and analyzing data

7. Documentation and record keeping

6.1 Determining the overhaul implementation scope and time

- To perform an overhaul process properly, first, the implementation scope and schedule must be determined. To this end, the operational units and engineering and repair departments shall perform needs assessments in this regard and inform the company’s managing director at least one year prior to the executive stage. The managing director shall review various aspects of the request, declare his/her approval and send the request to the headquarters. After obtaining the necessary permits (e.g. the board of directors resolution), the exact timetable of the overhaul process shall be announced to the production unit.

Note: The above process may change in accordance with the organizational structure of companies; however, the approval of the highest authority is essential.

- The safety of production facilities greatly depends on the health of machinery and equipment. This issue has always been considered as one of the main pillars of continuous production; therefore, the R&M Department as well as engineering, technical inspection and corrosion control departments [in accordance with their organizational tasks] shall continuously inspect all spare parts of different systems and provide necessary reports for subsequent planning to the Repair Planning Unit. These reports will provide the basis for future planning.

- The following factors can play a role in determining the implementation scope and time of the overhaul process:

- Considerable reduction in the production capacity of one or more units. As a result, the company may not be able to fulfill its commitments toward customers and stakeholders (stakeholders may be downstream companies)

- Reducing the efficiency of production equipment in one or more units, which leads to increased production costs and renders continuous production uneconomical

- Reducing the reliability and availability of production equipment in one or more units in a way that endangers the continuous production process.

- Monitoring and equipment performance measurement reports provided by operational units in previous overhaul operations.

- The mutual effects of the activities of different production units on each other.

- The effect of production cessation [caused by the overhaul process] on factors such as market status and company’s commitments towards customers (customers may be the downstream unit/companies of the main company).

- Occurrence of a major accident that may cease the production process.

- Suggestions provided by operational units on the basis of the final report of previous overhauls

- The volume of an overhaul operation depends on factors such as the number of equipment and operation complexity.

- In cases where an overhaul operation is postponed due to operational requirements, beyond the time specified in technical documents, risk assessment studies shall be necessary to assess the effect of this change on the whole system.

6.2 Timing

The Department of Planning specifies the time and scope of overhaul operations, uses project management software (e.g. Project-MS) to schedule the process and provides the R&M and HSE Departments with this information. This department shall also continuously monitor the progress of activities and inform relevant authorities of possible obstacles and non-compliance cases based on a comparison with the main schedule.

This schedule should include the following items:

1. A scheduled activity list with the exact implementation time

2. A manpower requirement list specifying job titles

3. A tools and machinery requirement list

4. Equipment and devices that must be put on the blanket list for overhaul in accordance with the P&ID drawings

6.3 HSE-Plan requirements

The Head of the HSE Department receives the overhaul timetable from the Planning Department, prepares an HSE-Plan and submits it to the executive manager/the head of the operational unit, before commencing overhaul operations. An HSE-Plan often contains the following:

- The training program for individuals and jobs in the activity list

- PPEs needed for various activities

- The list of normal and specific wastes

- List of safety and firefighting equipment needed for various activities

- The HSE manpower requirements

- Defining HSE requirements in accordance with the hazards and consequences of the overhaul operation

- In this plan, the responsibilities of safety officers and inspectors and firefighters should be clearly defined and all activities should be supervised completely.

- With regard to the number of hot works and prohibited areas, the Head of the HSE Department shall properly foresee, control and monitor required resources in such a way that:

- In restricted areas, one firefighter shall be present in the workplace permanently, up to the end of the work.

- In order to perform welding and flame cutting operations, one firefighter/safety officer shall be present in the workplace, until the end of the operation.

- Safety officers can [directly] supervise three simultaneous works, subjected to work permits, provided that the workplaces are not more than 50 meters apart.

The above issues may change in different companies depending on the available resources and the nature of companies, in order to further improve their safety measures.

6.4 Implementation

The tasks and responsibilities of different departments in the overhaul process are presented in the following paragraphs.

6.4.1 Repair groups

These groups should foresee the necessary tools and equipment to perform scheduled overhaul operations; observe safety requirements and guidelines such as scaffolding, excavation, working in confined spaces, etc. and attend relevant training courses in coordination with the HSE Department.

6.4.2 Head of the HSE Department

- Attending overhaul coordination meetings, as one of the main members and pursuing the implementation of relevant provisions

- Cooperation, coordination and consultation with relevant departments and units to facilitate the implementation of safety instructions

- Auditing the overhaul process to meet HSE requirements and ensuring full observance of all safety instructions through announced and surprise inspections

- Preparing emergency response plans (ERP) and determining emergency response teams

- Identification and analysis of accidents, near misses and unsafe acts/conditions and submitting reports to the chief executor, the head of the unit/department and other relevant authorities, at the beginning of each working day

- Submitting accident reports to the Operations Manager

- Hazard identification and risk assessment of overhaul-related jobs and activities in cooperation with relevant units and departments and planning to implement necessary corrective actions, e.g. Job Safety Analysis (JSA)

- Providing training courses for those involved in the overhaul process in cooperation with the Education Department and other relevant departments and units

- Coordination for temporary settlement of staff and offices in the vicinity of the site

- Inspecting equipment and machinery brought in to the site by the company or contractors in terms of technical health and safety

- Performing gas testing and other required tests for the issuance of work permits

- Full supervision over the issuance of work permits and their implementation in the following cases:

- The entry of special machinery into the site

- Working inside tanks, containers and confined spaces

- Working at height

- Excavation and trenching operations

- Welding and flame cutting

- Inspecting scaffolds and issuing relevant permits according to the scaffolding instruction

- Re-inspection of grounding systems in coordination with relevant departments

- Preparation and assurance of the availability of firefighting and rescue equipment (e.g. ambulance and health care teams)

- Identifying hazardous materials used and preparing their SDS and providing relevant personnel with essential trainings

- Holding joint meetings with the authorities of Repair Department and contractors to discuss safety issues

- Using safety and warning signs in areas where radiographic activity are carried out and preventing the entry of people into such areas in accordance with relevant instructions

- Designing warning panels, such as LUCK/SCAFF Tag/TAG OUT & UP and supervising their application by work groups in power lines, etc.

- Control and supervision of site cleaning and waste management (specially management of specific wastes)

- Controlling used tools and devices to ensure their proper function and technical health

6.4.3 Integrated Planning Department

The Integrated Planning Department, in coordination with other relevant departments and units, prepares the ground for verification and approval of the budget, requested by the Department of Planning, to carry out the overhaul process.

6.4.4 Logistics Department

In coordination with other repair departments/repair groups, the head of the Logistics Department shall take measures to purchase required spare parts, goods and consumables and supply necessary materials in order to avoid shortage of spare parts and goods during the overhaul process. It should be noted that the Head of the HSE Department may deem it necessary to examine all safety and firefighting equipment prior to purchase to ensure their compliance with available standards.

6.4.5 Repair Planning Department

The main tasks of this department include:

- Preparing lists of temporarily repaired equipment, which must be repaired thoroughly  during the overhaul process, and sending the list to the Technical Inspection Department

- Reviewing all the above lists and prioritizing activities during joint meetings with operational units and the HSE Department

- Compiling an overhaul manual, consisting of a list of process systems, equipment and activities and sending it to the HSE Department and the Integrated Planning Department for further review

- Receiving and processing feedbacks, finalizing the manual and re-communicating it

- Preparing the initial overhaul timetable

- Preparing lists of spare parts, equipment and consumables and sending them to the Logistics Department

- Estimating the budget required for the overhaul process and sending it to the Integrated Planning Department for funding approvals

- Coordinating with administrative, security and HSE units for fulfilling overhaul duties

- Providing and communicating the organizational chart to relevant organizational units and contractors

- Determining a partial overhaul plan that can adopted during the pre-overhaul timetable in joint meetings with operational and planning units

- Preparing the final overhaul timetable, including the activity list and man hour

- Announcing the beginning of the overhaul process by releasing the first repair notice

- Notifying repair work orders to executive groups

- Controlling tasks in accordance with relevant timetables and checklists

- Making changes in the overhaul plan (adding or removing items) after obtaining the approval of all relevant units

- Controlling and comparing daily progress with the overhaul schedule, preparing an S-Curve and reporting daily and cumulative progress reports of the overhaul process to the head of the operational unit or that of the operational area at the beginning of each working day to resolve possible problems

- Identifying existing difficulties and problems and holding urgent meetings to overcome these problems

6.4.6 Head of the operational unit

- Dividing operational units into separate process systems and announcing their titles and specifications to the Repair Planning Department/Unit

- Preparing a list of broken valves and submitting it to the Repair Planning Department

- Preparing a list of possible wastes, by specifying their type and weight, submitting the list to the HSE Department and sending a copy to the Repair Planning Department

- Preparing required work lists and sending them to the Repair Planning Department

- Preparing the list of required chemicals and catalysts, submitting it to the Logistics Department and sending copies to the HSE and Repair Planning Departments

- Preparing checklists to control the implementation of defined activities

- Preparing the list of high-risk activities and submitting it to the HSE Department

- Preparing the list of confined spaces in which overhaul activities have to be performed

- Sending repair requests to the Department of Planning

- Submitting a Blind List for equipment to the HSE Department to specify items that require entering into equipment (confined spaces) and obtain work permits therein

- Implementation of Pre-Overhaul stage

- Stopping the production process of operational units in accordance with the relevant Operational Manual

- Measures taken prior to the delivery of equipment to the Repair Department (e.g. depressurization of pipelines, etc.) in accordance with the relevant Operational Manual

- Confirming the integrity of the unit and temporary delivery of the unit to the Repair Department

- Issuing hot and cold work permits in coordination with the HSE Department and in accordance with relevant requirements

6.4.7 Head of the Technical Inspection and Corrosion Protection Department

- Preparing the list of relief valves’ calibration and sending it to the Repair Planning Department

- Sending the overhaul agenda to the Repair Planning Department

- Verifying the integrity of internal surfaces of equipment and reservoirs

- Verifying inspections and loading required catalysts

- Verifying the completion of technical inspection tasks

- Verifying the calibration and adjustment of instrumentation, analyzers and safety valves in accordance with available standards

- Obtaining necessary licenses for re-operation

Note: In cases where a direct administrator has not been appointed to perform the above tasks in a management/department/unit, the Managing Director shall appoint persons in similar positions (and with relevant expertise) to perform those tasks and notify other overhaul authorities.

6.4.8 General requirements

- The operational unit shall shut down and start up at the beginning and end of the overhaul process, respectively.

- Healthcare facilities and emergency medical services are essential for raising the preparedness level in coping with accidents. Emergency medical care teams must be permanently present in overhaul sites and ambulances must be available at all times. This issue should be approved by the HSE Department, before commencing the overhaul process.

- No one is permitted to stay at work for more than 12 hours. Relevant departments are primarily responsible for controlling this issue and the HSE Department shall supervise staff during the overhaul process and prevent and report infringements.

- Midday meals shall be provided for all regular (salaried) and contracting personnel involved in overhaul operations.

- Suitable dining facilities (e.g. place, air conditioning equipment, etc.) shall be provided for all regular and contracting personnel.

- The Security Department shall monitor and control the entry and exit of people and equipment using predetermined plans.

6.5 Completion of overhaul process, conducting tests and Pre-Startup Safety Review (PSSR)

- Machinery such as turbines, pumps, compressors, etc. should be restarted in accordance with their startup instructions.

- To ensure the proper implementation of the overhaul process and leakage tests, the Repair Department should conduct pre-startup safety reviews in accordance with the requirements of the Pre-Startup Safety Guideline (No. NIOC-HSE-SF-GU-002-01), before restarting equipment and delivering the site to the Operations Department.

6.6 Summarizing and analyzing data

The Repair Planning Department shall prepare a material balance report at the end of the overhaul process. Operating units and the HSE Department shall also prepare reports on overhaul operations within a maximum of two months and submit them to the Repair Department to be sent to the Repair Planning Department. This department shall then review and summarize these reports and hold post-overhaul meetings to inform the management and relevant organizational units about the implementation of the overhaul process, challenges, strengths and weaknesses, achievements and results.

The main topics of these meetings include:

- Reviewing and comparing the baseline program with the approved implemented program

- The actual organizational chart of the overhaul process

- A summary of all overhaul activities

- Executive problems and challenges

- Undone works

- Assessing the status of important equipment

- A summary of the most important activities

- A summary of HSE Department’s overhaul activities

- An analytical report of incidents

- Necessary corrective, preventive and remedial measures that need to be planned and implemented

- Total overhaul costs, including actual costs, opportunity costs, etc.

- Comparing total overhaul financial resources

- Calculating and interpreting key performance indices

- Predicting the schedule of the next overhaul operation

- Providing suggestions on future overhaul operations and plans

- A summary of relevant meetings and discussions shall be documented and provided to the following authorities by the Repair Planning Department:

- Operations Manager

- Head of Operational Unit or Company

- Head of Operations

- Head of Operations Unit

- Head of Repair Department

- Head of Technical Services

- Head of Integrated Planning Department

- Head of Technical Inspection and Corrosion Protection Department

- Head of HSE Department

- Head of Financial Affairs Department

- Head of Process Engineering and other relevant departments and units to respective organizational structures

6.6.1 Performance evaluation

To determine the success rate of the overhaul process in terms of operational and HSE issues, this process must be evaluated using the following indices:

- Productivity

This index indicates the effectiveness of the overhaul process and the production ratio in each overhauled unit [within 45 days after the completion of the overhaul process] to the allocated production. This index is calculated by the operational unit and should not be less than 1.

- Environmental index

The ratio of the manageable waste weight to the total waste weight generated during the overhaul process.  This index is calculated by the HSE Department.

- Safety indices

Indices such as Accident Frequency Rate (AFR) and Accident Severity Rate, which are calculated by the HSE Department

- Health indices

Indices such as the staff absenteeism rate and work-related diseases, which are calculated by the HSE Department

6.7 Documentation and record keeping

All relevant records shall be kept for a specified period of time (1 to 5 years).

7. References

1. The ISO-TS 29001 Standard

2. Field studies and documents available in oil, gas and petrochemical companies

8. Relevant documents:

- The Pre-Startup Safety Guideline (No. NIOC-HSE-SF-GU-002-01)

- The Contractors’ HSE Management Guideline (No. NIOC-HSE-SF-GU-005-01)

- The Management of Change Guideline (No. NIOC-HSE-SF-GU-007-00)

No. 17, Yaghma Alley, Jomhuri Eslami Avenue, Tehran.

Tel. 66726016	Fax 66709723	SMS 10007615

HSEE@NIOC.IR	HTTP://HSE.NIOC.IR